## Planned Change Data
| Effort (man hours) |  |  |  |  | Labour Cost (GBP)
Improvement | Planning | Concept | Production | Testing | Total | Planning | Concept | Production | Testing | Total
Client side prediction to remove lag | 133.3333 | 311.1111 | 444.4444 | 311.1111 | 1200 | 2400 | 7777.7778 | 11111.1111 | 4666.6667 | 25955.5556
Additional rounds (18 additional rounds) | 20 | 46.6667 | 66.6667 | 46.6667 | 180 | 360 | 1166.6667 | 1666.6667 | 700 | 3893.3333
Music and Sound Effects | 8.8889 | 20.7407 | 29.6296 | 20.7407 | 80 | 160 | 518.5185 | 740.7407 | 311.1111 | 1730.3704
Differentiator between group and individual objectives or their timers. E.g. do not have a group objective for the first 1 min of the game. | 8.8889 | 20.7407 | 29.6296 | 20.7407 | 80 | 160 | 518.5185 | 740.7407 | 311.1111 | 1730.3704
Player controls in-game tutorial | 13.3333 | 31.1111 | 44.4444 | 31.1111 | 120 | 240 | 777.7778 | 1111.1111 | 466.6667 | 2595.5556
Player character break apart feature | 4.4444 | 10.3704 | 14.8148 | 10.3704 | 40 | 80 | 259.2593 | 370.3704 | 155.5556 | 865.1852
Additional round interactable items, e.g. 'Industrial fan' upwards thrust zone. | 44.4444 | 103.7037 | 148.1481 | 103.7037 | 400 | 800 | 2592.5926 | 3703.7037 | 1555.5556 | 8651.8519
Additional mid-ground and back-ground assets | 22.2222 | 51.8519 | 74.0741 | 51.8519 | 200 | 400 | 1296.2963 | 1851.8519 | 777.7778 | 4325.9259
Improved menu background transitions | 4.4444 | 10.3704 | 14.8148 | 10.3704 | 40 | 80 | 259.2593 | 370.3704 | 155.5556 | 865.1852
Animated clouds to be improved | 8.8889 | 20.7407 | 29.6296 | 20.7407 | 80 | 160 | 518.5185 | 740.7407 | 311.1111 | 1730.3704
Totals | 268.8889 | 627.4074 | 896.2963 | 627.4074 | 2420 | 4840 | 15685.1852 | 22407.4074 | 9411.1111 | 52343.7037
Total per team member | 67.2222 | 156.8519 | 224.0741 | 156.8519 | 605
Weeks per team member (40 hr/w) | 1.6806 | 3.9213 | 5.6019 | 3.9213 | 15.125

## Unity Relay Costs
Assumption
- No individual player will exceed their free monthly allowance of 3Gb - therefore only cost is when exceeding the cap
Typical Play Session Stats |  |  | Year | Number of Units Sold | Cumulative Number of Players | Number of concurrent players | Cost of concurrent player > 50 (per month) | Monthly Data consumption (MB) | Free Data (cap in MB) | Net Data (MB) | Cost of data (per month) | Total Cost (per month) | Cost of concurrent players > 50 (per year) | Cost of data (per year) | Total Cost (per year)
Players | 4 |  | 1 | 3503 | 3503 | 351 | 38.528 | 469226.85 | 150000 | 319226.85 | 40.861 | 79.389 | 462.336 | 490.3324 | 952.6684
Duration | 30 | mins | 2 | 10510 | 14013 | 1402 | 173.056 | 1877041.35 | 150000 | 1727041.35 | 221.0613 | 394.1173 | 2076.672 | 2652.7355 | 4729.4075
Game Data Usage | 1071.6 | MB | 3 | 17516 | 31529 | 3153 | 397.184 | 4223309.55 | 150000 | 4073309.55 | 521.3836 | 918.5676 | 4766.208 | 6256.6035 | 11022.8115
Per Player Data Usage | 267.9 | MB | 4 | 17516 | 49045 | 4905 | 621.44 | 6569577.75 | 150000 | 6419577.75 | 821.706 | 1443.146 | 7457.28 | 9860.4714 | 17317.7514
|  |  | 5 | 17516 | 66561 | 6657 | 845.696 | 8915845.95 | 150000 | 8765845.95 | 1122.0283 | 1967.7243 | 10148.352 | 13464.3394 | 23612.6914
Assumed percentage of concurrent users | 10%
Assumed percetage of players playing every month | 12.5%
Assumed play sessions per month (on average) | 4
USD --> GBP FX Rate | 0.8
| USD | GBP
Cost per GB | 0.16 | 0.128
Cost per concurrent user above 50 | 0.16 | 0.128
|  |  | Year | Number of concurrent players | Total Cost (per year)
|  |  | 1 | 351 | 952.6684
|  |  | 2 | 1402 | 4729.4075
|  |  | 3 | 3153 | 11022.8115
|  |  | 4 | 4905 | 17317.7514
|  |  | 5 | 6657 | 23612.6914
Play data for a 10 minute, 4 player session

## Itch Fees
Year | Units Sold | Itch.io Cost
1 | 3503 | 1050.9
2 | 10510 | 3153
3 | 17516 | 5254.8
4 | 17516 | 5254.8
5 | 17516 | 5254.8

## Fixed and Variable Costs
Cost Estimations
Category | Item | Cost (£) | Comment
Setup Costs | Testing Hardware | 6000 | 4 x PC
| 3rd Party Assets | 100 | Approx cost
Labour Costs | Planning and Documenting | 18 | per hour
| Asset creation and Code | 25 | per hour - aslo used as cost of maintenance
| Testing | 15 | per hour
Recurring Expenditure | Development Environment | 4500 | 4 x Unity Licenses
| Itch.io Fee (5%) | 0.3 | 5% of £6 - per unit sold
| Unity Relay Fees - CCU | 0.128 | per CCU > 50 per month
| Unity Relay Fees - Bandwidth | 0.128 | per GB > 150 per month
| 25k Ad Impressions | 135 | per week (based on Facebook cost of $7.19 CPM)
Labour Costs
|  |  |  | Phase | Estimated Hours | Cost
|  |  |  | Planning | 268.8889 | 4840
|  |  |  | Concept | 627.4074 | 15685.1852
|  |  |  | Production | 896.2963 | 22407.4074
|  |  |  | Testing | 627.4074 | 9411.1111
[5 empty] | Total Labour Costs | 52343.7037
[5 empty] | Total Setup Costs | 6100
[5 empty] | Total Costs (excl. Maintenance & recurring expenditure) | 58443.7037
[5 empty] | Annual Maintenance @ approx 583 hr / year | 14550

## Yr One Timeline
[5 empty] | 2023 | [5 empty] | 2024
| Hours p/team |  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Phase | member | Start | End | Planning
Planning | 67.2222 | 2023-07-03 | 2023-07-15 | Concept
Concept | 156.8519 | 2023-07-15 | 2023-08-12 | Production
Production | 224.0741 | 2023-08-12 | 2023-09-21 | Testing
Testing | 156.8519 | 2023-09-21 | 2023-10-19 | Maintenance
Maintenance | 500 | 2023-10-19 | 2024-11-01
Formulas:
End = ROUNDUP([Start]+([Hours p/team]*7/40), 0)
Start = [End, row above]

## Estimated Revenue
Number of PC Gamers (Global) | 1700000000
% of gamers playing multiplayer | 56%
Number of PC Gamers (Multiplayer) | 952000000
% of casual multiplayer game players | 73.6%
Number of casual multiplayer players | 700672000
Estimated % interested in Construction Chaos | 0.5%
Construction Chaos target audience (max) | 3503360
Estimated % of target audience captured | 10%
Estimated number of target audience captured | 350336
|  |  | Assumed target audience size |  | Sell price (GBP)
|  |  | 350336 |  | 6
|  | Year | Adoption rate | Units Sold | Total Revenue
Base App
|  | Year 1 | 1% | 3503 | 21018
|  | Year 2 | 3% | 10510 | 63060
|  | Year 3 | 5% | 17516 | 105096
|  | Year 4 | 5% | 17516 | 105096
|  | Year 5 | 5% | 17516 | 105096

## Cost Walk
Phase | Increase
Yr 1 Revenue | 21018
Investment | 60000 |  | Assumed level of maintenance |  |  | 20%
Fixed Costs (one-off) | -6100
Planning | -4840
Concept | -15685.1852 |  | Yr1 | Yr2 | Yr3 | Yr4 | Yr5
Production | -22407.4074 | Start of Maintenance | 2023-10-19 | 2024-01-01 | 2025-01-01 | 2026-01-01 | 2027-01-01
Testing | -9411.1111 | End of Maintenance | 2023-12-31 | 2024-12-31 | 2025-12-31 | 2026-12-31 | 2027-12-31
Maintenance (117 hours) | -2925 | Days of maintenance | 73 | 365 | 364 | 364 | 364
Ad Costs (11 weeks) | -1485 | Weeks of maintenance | 11 | 53 | 52 | 52 | 52
Unity Relay | -952.6684 | Hours of maintenance | 117 | 584 | 582 | 582 | 582
Development Environment | -4500
Itch Fee (5%) | -1050.9
Yr1 Profit | 11660.7279
Yr 2 Revenue | 63060
Maintenance (584 hours) | -14600
Ad Costs (53 weeks) | -7155
Unity Relay | -4729.4075
Development Environment | -4500
Itch Fee (5%) | -3153
Yr 2 Profit | 40583.3203
Yr 3 Revenue | 105096
Maintenance (582 hours) | -14550
Ad Costs (52 weeks) | -7020
Unity Relay | -11022.8115
Development Environment | -4500
Itch Fee (5%) | -5254.8
Yr 3 Profit | 103331.7089
Yr 4 Revenue | 105096
Maintenance (582 hours) | -14550
Ad Costs (52 weeks) | -7020
Unity Relay | -17317.7514
Development Environment | -4500
Itch Fee (5%) | -5254.8
Yr 4 Profit | 159785.1574
Yr 5 Revenue | 105096
Maintenance (582 hours) | -14550
Ad Costs (52 weeks) | -7020
Unity Relay | -23612.6914
Development Environment | -4500
Itch Fee (5%) | -5254.8
Yr 5 Profit | 209943.6661
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## ROI
Investor Share | 40%
Investor GBP | 60000
Year | Net Profit | Investor Profit Share | ROI
1 | 11660.7279 | 4664.2911 | 7.774%
2 | 40583.3203 | 16233.3281 | 27.06%
3 | 103331.7089 | 41332.6835 | 68.89%
4 | 159785.1574 | 63914.063 | 106.5%
5 | 209943.6661 | 83977.4664 | 140%
| Total investor profit share | 210121.8322 | 350.2%
| Total investor profit, after investment | 150121.8322